## TimeLine
|  |  | April | [9 empty] | Mei
|  |  | Week 12 |  |  |  | Week 13 | [5 empty] | Week 14 | [6 empty] | Week 15 | [6 empty] | Week 16 | [6 empty] | Week 17
|  |  | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
Persiapan | Pemilihan Kasus dan Algoritma | Pemilihan Kasus | bar: Week 12 21 to Week 12 24
Penentuan Algoritma | bar: Week 12 21 to Week 12 24
Pelaksanaan | Business Understanding | Menentukan Objektif Bisnis | bar: Week 13 25 to Week 13 30
Menentukan Tujuan Bisnis | bar: Week 13 25 to Week 13 30
| Data Understanding | Mengumpulkan Data | bar: Week 14 1 to Week 14 6
Menelaah Data | bar: Week 14 1 to Week 14 6
Memvalidasi Data | bar: Week 14 1 to Week 14 6
| Data Preparation | Memilah Data | bar: Week 14 7 to Week 15 12
Membersihkan Data | bar: Week 14 7 to Week 15 12
mengkonstruksi Data | bar: Week 14 7 to Week 15 12
Menentukan Label Data | bar: Week 14 7 to Week 15 12
Menintegrasikan Data | bar: Week 14 7 to Week 15 12
| Machine Learning Pipeline | Membangun Skenario | bar: Week 15 13 to Week 16 17
Membangun Model | bar: Week 16 18 to Week 17 27
| Model Evaluation | Mengevaluasi Hasil Pemodelan | bar: Week 16 18 to Week 17 27
Melakukan Review Proses Pemodelan | bar: Week 16 18 to Week 17 27
| Deployment | melakukan Deploymen Model | bar: Week 16 18 to Week 17 27
Membuat laporan akhir Proyek | bar: Week 16 18 to Week 17 27
Sudah dikerjakan
Sedang dikerjakan
Belum dikerjakan